## Remaining Gaps
Mobile vs. Web Parity — Remaining Gaps
# | Gap | Detail | Area | Severity | Status | Notes
1 | JetBrains Mono not loaded on mobile | Web uses it for every citation, date and card title. Biggest single visual difference. | Typography | High | Not started
2 | Screens still on the old colour set | 50 screens on the old colours, only 11 migrated to the new screen-theme. | Theming | High | Not started
3 | Home screen doesn't match web | Out of order, uses a side-scroll carousel, and is missing the Featured Article card and the weekly activity chart. | Home | High | Not started
4 | Patterned background missing | Applied on only 3 screens; web uses it throughout. | Visual | Medium | Not started
5 | Two case-card components that have drifted apart | Duplicated component; needs consolidating into one. | Components | Medium | Not started
| Gaps closed | 0 of 5
Status values: Not started / In progress / Blocked / Done

## Plan
Delivery Plan
Day | Theme | Task | Outcome | Status | Notes
Tue | Foundations | Load JetBrains Mono | Nothing visible changes | Not started
Tue | Foundations | Build shared background + card components | Nothing visible changes | Not started
Tue | Foundations | Take fresh web reference screenshots (the ones in the repo are from Feb and already wrong) | Nothing visible changes | Not started
Wed | Home | Rebuild Home to web's order | Home matches web | Not started
Wed | Home | Replace carousel with a list | Home matches web | Not started
Wed | Home | Add Featured Article card and weekly activity chart | Home matches web | Not started
Thu | Cards & core screens | One case card everywhere — accent bar, mono meta, purple chips | Single case card in use | Not started
Thu | Cards & core screens | Restyle Laws | Single case card in use | Not started
Thu | Cards & core screens | Restyle Activity | Single case card in use | Not started
Fri | Sweep the rest | Nuggets | Remaining screens on new theme | Not started
Fri | Sweep the rest | Articles | Remaining screens on new theme | Not started
Fri | Sweep the rest | Bookmarks | Remaining screens on new theme | Not started
Fri | Sweep the rest | Folders | Remaining screens on new theme | Not started
Fri | Sweep the rest | Notes | Remaining screens on new theme | Not started
Fri | Sweep the rest | Subject matter | Remaining screens on new theme | Not started
Fri | Sweep the rest | Bye-laws | Remaining screens on new theme | Not started
Mon | Polish & QA | Settings sub-pages | Sign-off | Not started
Mon | Polish & QA | Ask DL resource chips | Sign-off | Not started
Mon | Polish & QA | Full QA — small and large phones, light and dark, big font | Sign-off | Not started
Mon | Polish & QA | Sign-off | Sign-off | Not started
| Tasks complete | 0 of 20
| % complete | 0%
Status values: Not started / In progress / Blocked / Done

## Lists (hidden)
Status | Source list for the Status dropdowns. Edit here to change the options everywhere.
Not started
In progress
Blocked
Done